## Ahmed Sharif
To-do list
To be completed by: |  | 2024-04-13 |  | Name: AHMED SHARIF
Deadline: |  | 2024-04-14 |  | Date: 4/3/2024
Project 2
Status | Task | Start By | End By | Original Due By | Number Of Days | Task Description
Completed | Planning | 2024-04-03 | 2024-04-03 | 2024-04-03 | 1 | Make sure all necessary preparations are completed.
Completed | Project Template and Preparation | 2024-04-04 | 2024-04-04 | 2024-04-04 | 1 | Devote time to thoroughly watch and comprehend the tutorial video provided, ensuring a strong foundational understanding of the project's objectives and requirements.
Completed | Setting up star schema | 2024-04-04 | 2024-04-04 | 2024-04-04 | 1 | Using the FileUpload.OriginallyLoadedData table and adding additional columns to the schema’s tables
Completed | Adding new table and adding columns | 2024-04-04 | 2024-04-06 | 2024-04-06 | 2 | Engage in an adding new four tables
Completed | Write stored procedures | 2024-04-06 | 2024-04-08 | 2024-04-08 | 2 | Delve into precedure of the project materials, absorbing critical information and insights necessary for successful project completion.
Completed | Create a stored procedure that returns the steps of our TrackWorkFlow procedure | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2 | Delve into precedure, absorbing critical information and insights necessary for successful project completion.
Completed | Creating Presentations | 2024-04-10 | 2024-04-11 | 2024-04-11 | 1 | Record the project presentations as per the specified requirements
Completed | Hand-off | 2024-04-11 | 2024-04-12 | 2024-04-12 | 1 | Ensuring the project's successful completion and delivery.
Completed | Follow-up | 2024-04-12 | 2024-04-13 | 2024-04-13 | 1 | Timely uploading of all completed project work to the group drive.

## Anmol Talwar
To-do list
To be completed by: |  | 2024-04-13 |  | Name: Anmol Talwar
Deadline: |  | 2024-04-14 |  | Date: 4/4/2024
Project 2
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-04-04 | 2024-04-04 | 2024-04-04 | 1 | Make sure all necessary comoponts such as JDBC are working proprerly and start reading the assignment instructions.
100% | Preparation & Meeting for work division. | 2024-04-05 | 2024-04-05 | 2024-04-05 | 1 | Download and install BiClass DB & meet with group to divide and plan the project work.
100% | Assignment Learning & Start off | 2024-04-05 | 2024-04-05 | 2024-04-05 | 1 | Clearly going through assignment resources and watching videos, reading topics needed for project. Also, start working on project
100% | Start planning out my work which is to Loadup the data from 1 table to another. | 2024-04-05 | 2024-04-07 | 2024-04-07 | 2 | Creating & implementing a proper plan for my work yp Load Up data from 1 table to another. Start writing code for it.
100% | Implementing and continue writing the code for my stored procedures. | 2024-04-07 | 2024-04-09 | 2024-04-09 | 2 | Continue writing up the code for my all 5 stored procedures which are Load DimCust From FileUpload Load DimMaritalStatus From FileUpload Load DimGender From FileUpload Load DimOccupation From FileUpload
100% | Collaborate with my member of group for 5th collaborated stored procedure. | 2024-04-09 | 2024-04-11 | 2024-04-11 | 2 | Collaborated with team member Constantinos to write code for 5th stored procedure [Project2].[CreateDimProduct_DimProductCategory_DimProductSubCategoryAndLoadData].
100% | Finishing up coding and prepare for recordings and submissions | 2024-04-11 | 2024-04-12 | 2024-04-12 | 1 | Finishing up all coding & reviewing it. Planning the recordings and preparing for all submissions required.
100% | Hand-off | 2024-04-12 | 2024-04-13 | 2024-04-13 | 1 | Recording all 3 presentations and all the work I did to submit to drive.
100% | Follow-up | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Uploading all the work to drive for project leader to submit & talking to group how they doing.

## Ashish Maharjan
To-do list
To be completed by: |  | 2024-04-13 |  | Name: Ashish Maharjan
Deadline: |  | 2024-04-14 |  | Date: 04/4/2024
Project 2
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-04-04 | 2024-04-04 | 2024-04-04 | 1 | Clearly outline the instruction which prof. gave and try to divide each work
100% | Preparation | 2024-04-05 | 2024-04-05 | 2024-04-05 | 1 | Download and install BiClass database from Blackboard. and make sure to check the tables of that database.
100% | Create Schema and tables with columns add up | 2024-04-06 | 2024-04-06 | 2024-04-06 | 1 | Arrange the starschema and add the four tables
100% | Create Process.usp_ShowWorkFlowSteps and Stored Procedure to load data | 2024-04-07 | 2024-04-08 | 2024-04-08 | 2 | Creating a stored procedure named usp_ShowWorkFlowSteps within the schema Process and another stored procedure for loading data.
100% | Drop or add foreign key and truncate all table | 2024-04-09 | 2024-04-11 | 2024-04-11 | 3 | Modify the foreign key constrains in the database schema. Drop foreign key and add foreign key and also empty all the tables in the database.
100% | Run in JDBC and give report to Group | 2024-04-11 | 2024-04-11 | 2024-04-11 | 1 | Use the JDBC driver created for project 1 and try to implement the code for this project and add the total execution time. after that check on Gp members how all doing.
100% | Paperwork and Presentation | 2024-04-11 | 2024-04-12 | 2024-04-12 | 2 | Create a Paperwork for the JDBC presentation and after that do the presentation.
100% | Hand-off | 2024-04-12 | 2024-04-12 | 2024-04-12 | 1 | Check on all the group members and revise all the work and make sure my everywork is in my folder
100% | Follow-up | 2024-04-13 | 2024-04-13 | 2024-04-13 | 1 | Upload everything from the folder to the Drive and let group members know about it to check my work.

## Benjamin Zhong
To-do list
To be completed by: |  | 2024-04-13 |  | Name: Benjamin Zhong
Deadline: |  | 2024-04-14 |  | Date: 4/4/2024
Project 2
% done | Task | Start By | Original Due By2 | Revised Due By | Number Of Days | Notes & Revision Notes
100% | Planning | 2024-04-04 | 2024-04-04 | 2024-04-04 | 1 | Official start to my project, we had a meeting call on the same thursday
100% | Meeting 1 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 1 | Meeting 1 was a project overview, getting everyone onboard for the overall goal of the project. We also divided the stored procedures
100% | Create User Authorization Stored Procedures + UserAuth Table data added / date last updated | 2024-04-04 | 2024-04-08 | 2024-04-08 | 4 | Work on individual procedures and get help from groupmates when needed
100% | Meeting 2 | 2024-04-08 | 2024-04-08 | 2024-04-08 | 1 | Meeting 2 was a check-in on everyone's stored procedures
100% | Upload.DimOrderDate from FileUpload | 2024-04-09 | 2024-04-12 | 2024-04-12 | 3 | Work on individual procedures and get help from groupmates when needed
100% | Meeting 3 | 2024-04-12 | 2024-04-12 | 2024-04-12 | 1 | Final Check-in begin finising touches of draft submission
100% | Upload DimTerritory from FileUpload | 2024-04-12 | 2024-04-12 | 2024-04-12 | 1 | Finalize stored procedures and finish the last two fileupload procedures
100% | Draft Submission | 2024-04-12 | 2024-04-12 | 2024-04-13 | 8 | Draft Submission was pushed back due to missing recordings, and testing from our WorkFlowStepsTableRowCount errors
100% | Final Submission | 2024-04-13 | 2024-04-13 | 2024-04-14 | 1 | Final Submission was revised to accomodate for adding the voice annotations to our powerpoints

## Constantinos Cleanthous
To-do list
To be completed by: |  | 2024-04-13 |  | Name: Constantinos Cleanthous
Deadline: |  | 2024-04-14 |  | Date: 4/3/2024
Project 2
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-04-05 | 2024-04-05 | 2024-04-05 | 1 | Meet with the group, outline what the project needs, begin talking about roles between groupmates
100% | Preparation | 2024-04-05 | 2024-04-05 | 2024-04-05 | 1 | Download and install the Bclass database
100% | Work on Procedures | 2024-04-06 | 2024-04-06 | 2024-04-06 | 1 | Work on the [CreateSequenceKeysForTables]
100% | Work on Procedures (conti.) | 2024-04-07 | 2024-04-08 | 2024-04-08 | 2 | Work on the [AlterTableIdentityKeystoSequenceObjects]
100% | Work on Procedures (conti.) | 2024-04-09 | 2024-04-11 | 2024-04-11 | 3 | Work on the [Load_SalesManagers]
100% | Work on Procedures (conti.) | 2024-04-11 | 2024-04-11 | 2024-04-11 | 1 | Work on the [CreateDimProduct_DimProductCategory_DimProductSubCategoryAndLoadData]
100% | Paperwork | 2024-04-11 | 2024-04-11 | 2024-04-12 | 1 | Work on the slides, and the JDBC code for my procedures; Do recordings for my slides
100% | Hand-off | 2024-04-12 | 2024-04-12 | 2024-04-12 | 1 | Send all the information, and recordings to group leader
100% | Follow-up | 2024-04-13 | 2024-04-13 | 2024-04-13 | 1 | Finalize everything with the group